Recycler.IQ

Product Roadmap (Multi-Repo)

Now / Next / Later  |  Updated: April 2026

# Repositories

recycleriq-core — Domain, Common (NuGet packages)

recycleriq-cloud — API, Application, Infrastructure, Web.Portal

recycleriq-clients — UI.Shared, UI.TaxAuthority, UI.RetailClient, UI.WebClient

recycleriq-link — Hardware, Link.Service

recycleriq-simulator — Standalone Blazor Server simulator (post-MVP)

# Status Overview

4 critical decisions pending (billing, sync strategy, grace period, ML approach)

0 items in progress — foundation build has not started

2 items partially complete from POC (SimulatorRecyclerClient, KisanRecycler partial)

Tax Authority first, Retail second

# Now — Decide & Foundation Build

Resolve critical decisions and establish the multi-repo foundation across all 5 repositories.

| Item | Status | Owner | Depends On |
| --- | --- | --- | --- |
| Critical Decisions (Blockers) |  |  |  |
| Select billing platform (QuickBooks vs Salesforce) | Evaluating | Tommy | None |
| Define sync conflict resolution strategy | Not Started | Tommy | None |
| Define license grace period duration | Not Started | Tommy | None |
| Finalize permission matrix | In Progress | Tommy | None |
| Foundation Build (Multi-Repo Setup) |  |  |  |
| Set up recycleriq-core repo (Domain, Common NuGet packages) | Not Started | Dev Team | None |
| Build RecyclerIQ.Domain (entities, enums, interfaces) | Not Started | Dev Team | recycleriq-core repo |
| Build RecyclerIQ.Common (shared utilities, DTOs) | Not Started | Dev Team | recycleriq-core repo |
| Set up recycleriq-cloud repo (API, Application, Infrastructure, Web.Portal) | Not Started | Dev Team | recycleriq-core published |
| Build RecyclerIQ.Infrastructure (EF Core, Azure SQL, schema-per-tenant) | Not Started | Dev Team | recycleriq-cloud repo |
| Build RecyclerIQ.API skeleton (auth, tenant middleware, base endpoints) | Not Started | Dev Team | Infrastructure |
| Set up observability (Serilog + OpenTelemetry + Seq dev backend) | Not Started | Dev Team | API skeleton |

# Next — Tax Authority Launch

Build all Tax Authority components: Link.Service, UI.TaxAuthority, Web Portal Phase 1, sync, license, installer. Validates shared infrastructure for all future work.

| Item | Status | Owner | Depends On |
| --- | --- | --- | --- |
| Tax Authority Launch (Phase 1 Go-to-Market) |  |  |  |
| Set up recycleriq-link repo (Hardware, Link.Service) | Not Started | Dev Team | Foundation build |
| Port Link.Service (from POC) to production architecture | Not Started | Dev Team | recycleriq-link repo |
| Complete RecyclerIQ.Hardware (IRecycler, SimulatorRecyclerClient, KisanRecycler) | Not Started | Dev Team | recycleriq-link repo |
| Build sync endpoints (transactions, inventory, heartbeat, users, config) | Not Started | Dev Team | API skeleton, Conflict resolution decision |
| Build license system (IBillingService, JWT issuance, validation, grace period) | Not Started | Dev Team | Billing platform decision, Grace period decision |
| Set up recycleriq-clients repo (UI.Shared, UI.TaxAuthority, UI.RetailClient, UI.WebClient) | Not Started | Dev Team | Foundation build |
| Build RecyclerIQ.UI.TaxAuthority (Login, Collector, Inventory, Daily Summary pages) | Not Started | Dev Team | UI.Shared, Link.Service |
| Build RecyclerIQ.UI.Shared component library (PIN keypad, inventory grid, receipts) | Not Started | Dev Team | recycleriq-clients repo |
| Build Web Portal Phase 1 (auth, shared admin pages, Tax Authority dashboard/reports) | Not Started | Dev Team | API complete, Reporting endpoints |
| Build ClickOnce-style installer/bootstrapper | Not Started | Dev Team | Device registry API, License system |

# Later — Retail & Post-MVP

Retail inherits all shared infrastructure. ML and additional features are strategic bets.

| Item | Status | Owner | Depends On |
| --- | --- | --- | --- |
| Retail Launch (Phase 2) |  |  |  |
| Build RecyclerIQ.UI.RetailClient (shift model, deposits, withdrawals, transfers) | Not Started | Dev Team | Tax Authority launch |
| Build Web Portal Phase 2 (Retail dashboard, CIT reports, shift reports) | Not Started | Dev Team | Portal Phase 1 |
| Post-MVP / Future |  |  |  |
| ML forecasting engine (cash depletion/overflow prediction) | Not Started | TBD | ML approach decision |
| Set up recycleriq-simulator repo (standalone Blazor Server simulator) | Not Started | TBD | Post-MVP |
| Additional recycler manufacturers | Not Started | TBD | Manufacturer scope decision |
| Custom permission groups | Not Started | TBD | Retail launch |