# Recycler.IQ Product Roadmap

Version 1.0 | Last Updated: 2026-04-06

Status: Sprint 1 in progress (RCORE substantially complete, RCLIENT 50% complete, RCLOUD/RLINK/RIQSIM in backlog)

## Executive Summary

| Metric | Count |
| --- | --- |
| Total Epics | 31 |
| In Progress | 6 |
| Backlog | 25 |
| Completed | 0 |
| At Risk | 0 |

Projects Status Overview:

| Project | Epics | In Progress | Backlog | Status |
| --- | --- | --- | --- | --- |
| RCORE | 2 | 2 | 0 | ✅ Substantially Complete |
| RCLIENT | 9 | 4 | 5 | 🟡 50% Complete |
| RCLOUD | 10 | 0 | 10 | 🔴 Not Started |
| RLINK | 8 | 0 | 8 | 🔴 Not Started |
| RIQSIM | 2 | 0 | 2 | 🔴 Not Started |

## Sprint 1 Roadmap (Current: Mar 29 — Apr 19, 2026)

### RCORE — Repository & Domain Foundation

Status: ✅ On Track (Substantially Complete)

Core shared packages foundation for all projects.

| Epic Key | Epic Title | Status | Details |
| --- | --- | --- | --- |
| RCORE-94 | RIQ-CORE-E01: Repository & Package Setup | 🟢 In Progress | Repo scaffolded, CI pipeline live, SemVer configured, GitHub Packages NuGet feed operational |
| RCORE-95 | RIQ-CORE-E02: Domain Model | 🟢 In Progress | Full domain model: 6 aggregates, 10 entities, 5 value objects, 6+ domain events, 7 enums, test coverage complete |

Dependencies: None (foundational) Blockers: None Key Decisions: - NuGet feed: GitHub Packages (not Azure Artifacts) - CI: GitHub Actions - Solution format: .slnx (new XML format) - Auth hashing: PBKDF2 (SHA256, 100K iterations)

### RCLIENT — Client Applications (MAUI + Blazor)

Status: 🟡 On Track (50% Complete)

MAUI Blazor Hybrid clients for TaxAuthority and Retail, plus Blazor Server web client.

| Epic Key | Epic Title | Status | Details |
| --- | --- | --- | --- |
| RCLIENT-1 | RIQ-CLIENT-E01: Repository & Project Setup | 🟢 In Progress | Repo scaffolded, solution structure (UI.TaxAuthority, UI.RetailClient, UI.WebClient, UI.Shared), MudBlazor 9.2.0 integrated |
| RCLIENT-2 | RIQ-CLIENT-E02: Local Client Auth Architecture | 🟢 In Progress | LocalIdentityProvider (PIN + password), RiqAuthenticationStateProvider, DI wiring for demo mode complete, 4 unit tests |
| RCLIENT-4 | RIQ-CLIENT-E04: Demo Mode Features | 🟢 In Progress | DemoDataSeeder (30 days sample data), DemoResetService functional; AppModeOptions partial (class exists, not yet bound to appsettings) |
| RCLIENT-5 | RIQ-CLIENT-E05: WebClient (Blazor Server) | 🟢 In Progress | Blazor Server project scaffolded with MudBlazor, layout shell, template pages; AppModeOptions & UI.Shared wiring TBD |
| RCLIENT-3 | RIQ-CLIENT-E03: Tax Authority Local UI | 🔴 Backlog | Blocked on E01, E02 completion |
| RCLIENT-6 | RIQ-CLIENT-E06: Self-Serve Demo Provisioning | 🔴 Backlog | Blocked on E04, cloud integration |
| RCLIENT-7 | RIQ-CLIENT-E07: Retail Local UI | 🔴 Backlog | Blocked on E01, E02 completion |
| RCLIENT-8 | RIQ-CLIENT-E08: Installer & Client Distribution | 🔴 Backlog | Blocked on all client UI epics |
| RCLIENT-9 | RIQ-CLIENT-E09: Shared UI Component Library | 🔴 Backlog | Cross-cutting, needed by all clients |

Key Risks: - AppModeOptions not yet wired to appsettings.json/CLI args (low risk, on track to fix) - WebClient UI.Shared integration incomplete (expected in next sprint)

Dependencies: RCORE (domain/common packages), Link.Service (runtime), Cloud API (future integration)

### RCLOUD — Cloud API & Portal

Status: 🔴 Not Started

Central API, web portal analytics, admin, and reporting.

| Epic Key | Epic Title | Status |
| --- | --- | --- |
| RCLOUD-1 | RIQ-CLOUD-E01: Repository & Infrastructure Setup | 🔴 Backlog |
| RCLOUD-2 | RIQ-CLOUD-E02: Authentication & Multi-Tenancy (Cloud) | 🔴 Backlog |
| RCLOUD-3 | RIQ-CLOUD-E03: Identity Provider & Auth Paths (Cloud) | 🔴 Backlog |
| RCLOUD-4 | RIQ-CLOUD-E04: Database Architecture & Tenant Routing | 🔴 Backlog |
| RCLOUD-5 | RIQ-CLOUD-E05: Cloud API Core | 🔴 Backlog |
| RCLOUD-6 | RIQ-CLOUD-E06: Edge Sync Engine | 🔴 Backlog |
| RCLOUD-7 | RIQ-CLOUD-E07: License & Billing System | 🔴 Backlog |
| RCLOUD-8 | RIQ-CLOUD-E08: Web Portal | 🔴 Backlog |
| RCLOUD-9 | RIQ-CLOUD-E09: CIT Management | 🔴 Backlog |
| RCLOUD-10 | RIQ-CLOUD-E10: ML & Forecasting Engine | 🔴 Backlog |

Dependencies: RCORE (domain packages), RCLIENT (API consumers)

Start Date: After RCLIENT E04 & E05 complete (projected: early May)

### RLINK — Edge Service & Hardware Abstraction

Status: 🔴 Not Started

Site-level agent for hardware comms, sync, license validation.

| Epic Key | Epic Title | Status |
| --- | --- | --- |
| RLINK-1 | Link.Service Core | 🔴 Backlog |
| RLINK-2 | Hardware Abstraction Layer | 🔴 Backlog |
| RLINK-3 | Sync & Background Services | 🔴 Backlog |
| RLINK-4 | gRPC & .proto Contracts | 🔴 Backlog |
| RLINK-5 | Cloud SignalR Integration | 🔴 Backlog |
| RLINK-6 | API Key Authentication | 🔴 Backlog |
| RLINK-7 | Multi-Recycler State Management & Failover | 🔴 Backlog |
| RLINK-8 | Repository & Service Setup | 🔴 Backlog |

Dependencies: RCORE (domain packages), RCLIENT (gRPC contract), RCLOUD (signalr integration)

Start Date: After RCLIENT complete (projected: late May)

### RIQSIM — Standalone Hardware Simulator

Status: 🔴 Not Started

Blazor Server + REST API simulator for development and demo without hardware.

| Epic Key | Epic Title | Status |
| --- | --- | --- |
| RIQSIM-1 | Repository & Project Setup | 🔴 Backlog |
| RIQSIM-2 | Simulator Engine & REST API | 🔴 Backlog |

Dependencies: RCORE (domain packages), RLINK (hardware abstraction interface)

Start Date: Parallel with RLINK (projected: late May)

## Release Timeline (Projected)

| Milestone | Target Date | Deliverables |
| --- | --- | --- |
| Sprint 1 Complete | 2026-04-19 | RCORE done, RCLIENT 100% done, foundation ready for cloud |
| Sprint 2-3 (Cloud Phase) | 2026-05-31 | RCLOUD + RLINK 80% complete |
| Beta Release | 2026-06-30 | Tax Authority demo ready, Retail follow |
| v1.0 Release | 2026-07-31 | GA with all major epics complete |

## Key Assumptions & Risks

Assumptions: - Team remains 3 full-time developers - No major scope changes mid-sprint - Azure infrastructure provisioned and access granted - KISAN America partnership negotiations finalize by May 15

Risks: - Timeline Risk (Low): Cloud phase (RCLOUD) is estimated at 4-6 weeks; delays here impact GA - Dependency Risk (Low): RLINK depends on RCLIENT gRPC contracts; currently on track - Integration Risk (Medium): Multi-system integration (cloud + edge + clients) begins in Sprint 2; recommend integration testing plan now - Resource Risk (Low): Team is stable, but Link.Service work (RLINK) may require specialized hardware knowledge

## Capacity & Next Steps

Current Sprint Capacity: ~120 story points (RCORE ~25, RCLIENT ~95) Projected Sprint 2 Capacity: ~140 story points (RCLOUD ~80, RLINK ~60, RIQSIM ~20)

Next Actions: 1. Complete RCLIENT E05 (WebClient) by Sprint 1 end 2. Finalize RCLOUD E01 & E04 (repo + database) design docs by Apr 26 3. Plan RLINK kickoff; identify hardware test environment needs 4. Schedule Compass component reviews (all 10 components need Compass setup) 5. Monitor gRPC contract evolution as RCLIENT E02 matures

## Document Status

Source of Truth: This markdown file (RecyclerIQ_Roadmap.md) Sync Rule: When this file is updated, the corresponding .docx files must be regenerated: - Product_Roadmap.docx - RecyclerIQ_Roadmap.docx

Last Synced: 2026-04-06 (generating both .docx versions)