# Recycler.IQ — Tax Authority Demo Roadmap

Sprint 1 Status & Path to Demo (May 2026)

## Sprint Status Summary

| Status | Count | Percentage |
| --- | --- | --- |
| Done | 17 | 26% |
| In Progress | 4 | 6% |
| Selected for Development | 44 | 68% |
| TOTAL | 65 | 100% |

## Project Breakdown by Status

| Project | Done | In Progress | Selected for Dev | Total |
| --- | --- | --- | --- | --- |
| RCORE | 11 | 4 | 0 | 15 |
| RCLIENT | 6 | 0 | 22 | 28 |
| RLINK | 0 | 0 | 17 | 17 |
| RIQSIM | 0 | 0 | 5 | 5 |
| TOTAL | 17 | 4 | 44 | 65 |

## Now / Next / Later Phases

### Now: Sprint 1 (Mar 29 — Apr 19, 2026)

Complete RCORE domain foundation; kickstart RCLIENT AppModeOptions; establish RLINK and RIQSIM scaffolds.

RCORE Domain Model: 15 stories (11 Done, 4 In Progress) — 75% complete. Domain entities and identity/auth types being finalized for RCLIENT integration.

RCLIENT Demo Client: 28 stories (6 Done, 22 Selected for Dev) — 21% complete. AppModeOptions and emulator deployment in scope for Sprint 1. Login UI and transaction capture queued for Sprint 2.

RLINK & RIQSIM: 22 stories (all Selected for Dev) — Phase 0 scaffolding to begin. Hardware abstraction and in-memory simulator engine are critical path items.

### Next: Sprint 2 (Apr 19 — May 3, 2026)

Complete login and transaction capture UI; finalize RLINK hardware abstraction; build out RIQSIM REST API. RCORE domain fully locked. All client-facing features demo-ready by May 3.

### Later: Final Push (May 3 — May 10, 2026)

Integration testing, performance optimization, bug fixes, and demo rehearsal. Target: Tax Authority demo ready by May 10.

## Risks and Dependencies

Critical Path Items:

RCORE domain completion (Apr 19) — Identity/auth types must be stable before RCLIENT integration.

RCLIENT login UI (Apr 19—May 3) — PIN login and transaction UI are gating items for end-to-end demo.

RLINK hardware abstraction (Apr 19—May 3) — Device registry and request/response contract must support simulator-driven testing.

RIQSIM REST API (Apr 19—May 3) — Headless simulator state machine and API endpoints are unblocking integration.

Key Risks:

RLINK complexity — Mitigate by starting with simple in-memory device registry; defer Phase 1 (sync, observability) to post-demo.

RIQSIM race conditions — Use async/await and message queue patterns; unit test state machine extensively.

RCLIENT UI responsiveness — Profile with 100 concurrent transactions; optimize data binding and rendering.

Domain model schema lock-in — Finalize RCORE contracts by Apr 19; no breaking changes after.

## Success Criteria

By May 10, 2026 (Tax Authority Demo):

RCLIENT MAUI app deploys to Windows emulator

Tax cashier can log in with PIN

System accepts cash input via simulator device

Real-time transaction progress visible on screen

Change dispensing calculation runs and displays

No unhandled exceptions during demo scenario

Scenario completes in under 3 minutes end-to-end